## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME | SM/14534 | New | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 1494/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 41.61 | 0 | 0 | 0
2 | BIRBHUM | Nanoor | Birbhum Division | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME | SM/14534 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BRAHAMAKHANDA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | AE | JE4 | ORD/000732/2022-2023 | 221/BSD | 07/06/2022 | 04/12/2022 | RADIANT | 4.94 | 4.23 | 85.48 | 100
3 | BIRBHUM | Nanoor | Birbhum Division | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME | SM/14534 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BRAHAMAKHANDA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - B) | AE | JE4 | ORD/000733/2022-2023 | 298/BSD | 10/08/2022 | 08/11/2022 | RADIANT | 1.82 | 1.6 | 88.11 | 100
4 | BIRBHUM | Nanoor | Birbhum Division | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME | SM/14534 | New | Material Requisition To Resource Division |  |  | RTOR000054/2024-2025 | 3265/BHM | 02/12/2024 | 02/12/2024 | Resource Division | 14.05 | 0 | 0 | 0
5 | BIRBHUM | Nanoor | Birbhum Division | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME | SM/14534 | New | Different works related to water supply scheme at BRAHMANKHANDA PIPED WATER SUPPLY SCHEME (TSM/015460) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | Assistant Engineer | JE2 ,JE3 | ORD/000150/2024-2025 | 2598/BHM | 10/09/2024 | 10/09/2025 | ASHOK MITRA | 463.91 | 0 | 0 | 20
6 | BIRBHUM | Nanoor | Bolpur Mechanical | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME | SM/14534 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Brahmankhnda Water supply Scheme (T/W-I & II), Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000966/2024-2025 | 4535/BOL.MD | 20/12/2024 | 19/04/2025 | SATYAJIT GHOSH | 75.35 | 0 | 0 | 50
7 | BIRBHUM | Nanoor | Central Drilling | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME | SM/14534 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21941.45 | 5.83 | 0.03