## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Birbhum Division | Barshal piped water supply scheme. | SM/14535 | New | Material Requisition To Resource Division |  |  | RTOR000137/2023-2024 | 1557/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 407.86 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Barshal piped water supply scheme. | SM/14535 | New | Supply & Installation of Low lift Pumping Mchinery and other allied work for BARSHAL & Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000871/2023-2024 | 3388/BOL.MD | 16/10/2023 | 14/01/2024 | UNIVERSAL ENTERPRISES | 50.94 | 0 | 0 | 30
3 | BIRBHUM | Rampurhat-I | Birbhum Division | Barshal piped water supply scheme. | SM/14535 | New | Accetance cum Work Order For Supply and delivery of Sluice Valve for Barshal piped water supply scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte | AE(HQ) | Estimator,JE1 | ORD/000636/2023-2024 | 947/BHM | 14/03/2024 | 13/04/2024 | SSPR VALVE MANUFACTURING PVT LTD | 9.32 | 0 | 0 | 100
4 | BIRBHUM | Rampurhat-I | Birbhum Division | Barshal piped water supply scheme. | SM/14535 | New | Material Requisition To Resource Division |  |  | RTOR000219/2023-2024 | 236/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 3.08 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-I | Birbhum Division | Barshal piped water supply scheme. | SM/14535 | New | Different works related to water supply scheme at BARSHAL & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1,JE3 | ORD/000266/2023-2024 | 3506/BHM | 10/08/2023 | 15/09/2025 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 1024.06 | 0 | 0 | 30
6 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Barshal piped water supply scheme. | SM/14535 | New | Supply & Installation of High lift Pumping Mchinery and other allied work for BARSHAL & Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000873/2023-2024 | 3370/BOL.MD | 11/10/2023 | 31/07/2025 | SUNIL RABIDAS | 87.29 | 0 | 0 | 0
Total | [13 empty] | 1582.55 | 0 | 0