## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Bautia piped water supply scheme | SM/14536 | New | Supply & Installation of Low lift pumping machineries and other allied works for Bautia piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000927/2023-2024 | 3559/BOL.MD | 04/12/2023 | 01/04/2025 | M/S. UTTAM KUMAR CHATTERJEE | 24.37 | 11.31 | 46.39 | 40
2 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Bautia piped water supply scheme | SM/14536 | New | Supply & Installation of High lift pumping machineries and other allied works for Bautia piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000925/2023-2024 | 3558/BOL.MD | 04/12/2023 | 03/03/2024 | R. N. S. TRADING | 91.5 | 0 | 0 | 0
3 | BIRBHUM | Nalhati-I | Birbhum Division | Bautia piped water supply scheme | SM/14536 | New | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 1505/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 433.77 | 0 | 0 | 0
4 | BIRBHUM | Nalhati-I | Birbhum Division | Bautia piped water supply scheme | SM/14536 | New | Sinking of 200 X 200 mm Dia (through) and 125 m deep tubewell, 02 nos, 5.90 m X 4.10 m Chlorine room with sanitary arrangements, 300 CuM OHR & 150 cum OHR, 200 Cum CWR, Boundary wall with Gate, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Bautia & its adjoining mouzas water supply scheme within Nalhati-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000191/2024-2025 | 2772/BHM | 30/09/2024 | 30/09/2025 | M/S GHOSH AND CO. | 887.39 | 21.66 | 2.44 | 2
5 | BIRBHUM | Nalhati-I | Birbhum Division | Bautia piped water supply scheme | SM/14536 | New | Material Requisition To Resource Division |  |  | RTOR000048/2024-2025 | 3262/BHM | 02/12/2024 | 02/12/2024 | Resource Division | 21.17 | 0 | 0 | 0
6 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Bautia piped water supply scheme | SM/14536 | New | Quotation for new service connection at Bautia (Block - Nalhati-I Block) |  |  | BILL/01806/2024-2025 |  | 26/03/2025 | 26/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.04 | 0 | 0 | 0
Total | [13 empty] | 1472.24 | 32.97 | 2.24