## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Suri-I | Bolpur Mechanical | Siur Piped Water Supply Scheme. | SM/14537 | New | Providing electro-mechanical accessories and others for Siur & Adjoining Moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Driller in Charge | Junior Engineer | ORD/000771/2022-2023 | 306/Bol.MD | 23/03/2023 | 23/03/2024 | M. S. ENTERPRISE | 90.15 | 0 | 0 | 0
2 | BIRBHUM | Suri-I | Birbhum Division | Siur Piped Water Supply Scheme. | SM/14537 | New | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 1384/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 193.96 | 0 | 0 | 0
3 | BIRBHUM | Suri-I | Birbhum Division | Siur Piped Water Supply Scheme. | SM/14537 | New | Material Requisition To Resource Division |  |  | RTOR000188/2023-2024 | 3280/BHM | 27/07/2023 | 27/07/2023 | Resource Division | 2.56 | 0 | 0 | 0
4 | BIRBHUM | Suri-I | Bolpur Mechanical | Siur Piped Water Supply Scheme. | SM/14537 | New | Providing electro mechanical accessories and others for Siur and Adjoining Mouzas Water Supply Scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III,Driller in Charge | Junior Engineer | ORD/000783/2022-2023 | 318/BOL.M.D | 27/03/2023 | 27/03/2024 | M. S. ENTERPRISE | 90.15 | 49.61 | 55.03 | 60
5 | BIRBHUM | Suri-I | Birbhum Division | Siur Piped Water Supply Scheme. | SM/14537 | New | Different works for SIUR & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000083/2023-2024 | 1440/BHM | 25/04/2023 | 28/11/2025 | MUKHERJEE CONSTRUCTION | 777.14 | 259.21 | 33.35 | 15
Total | [13 empty] | 1153.95 | 308.82 | 26.76