## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Bolpur Mechanical | PARULIA PIPED WATER SUPPLY SCHEME. | SM/14538 | New | Providing electro-mechanical accessories and others for Parulia & adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000053/2023-2024 | 1060/Bol.MD | 08/06/2023 | 08/06/2024 | CINZANO | 69.83 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Birbhum Division | PARULIA PIPED WATER SUPPLY SCHEME. | SM/14538 | New | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 1402/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 193.54 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Birbhum Division | PARULIA PIPED WATER SUPPLY SCHEME. | SM/14538 | New | Different works related to water supply scheme at PARULIA, KHANPUR & PADUMA and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE,JE3 | ORD/000076/2023-2024 | 1425/BHM | 25/04/2023 | 30/06/2026 | BIPIN KUMAR SINGH | 2248.63 | 338.14 | 15.04 | 55
4 | BIRBHUM | Dubrajpur | Birbhum Division | PARULIA PIPED WATER SUPPLY SCHEME. | SM/14538 | New | Laying of distribution system and road restoration at Parulia Piped Water Supply Scheme, Dubrajpur Block, under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE | JE3 | ORD/000271/2025-2026 | 2417/BHM | 18/09/2025 | 17/12/2025 | BIPIN KUMAR SINGH | 68.09 | 0 | 0 | 0
5 | BIRBHUM | Dubrajpur | Birbhum Division | PARULIA PIPED WATER SUPPLY SCHEME. | SM/14538 | New | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 200 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION KACHUJORE-SIURI AT KM 48/7-9 OF ASANSOL DIVISION, EASTERN RAILWAY. |  |  | BILL/00956/2024-2025 | BP-2024-25-349 | 04/12/2024 | 04/12/2024 | EASTERN RAILWAY | 4.97 | 0 | 0 | 0
6 | BIRBHUM | Dubrajpur | Bolpur Mechanical | PARULIA PIPED WATER SUPPLY SCHEME. | SM/14538 | New | Quotation for new service connection at Parulia PWSS under Suri West CCC at Dubrajpur Block |  |  | BILL/00055/2025-2026 | 98/19 | 17/07/2025 | 17/07/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.26 | 0 | 0 | 0
Total | [13 empty] | 2593.33 | 338.14 | 13.04