## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Bolpur Mechanical | PARULIA PIPED WATER SUPPLY SCHEME. | SM/14538 | New | Providing electro-mechanical accessories and others for Parulia & adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000053/2023-2024 | 1060/Bol.MD | 08/06/2023 | 08/06/2024 | CINZANO | 69.83 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Birbhum Division | PARULIA PIPED WATER SUPPLY SCHEME. | SM/14538 | New | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 1402/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 193.54 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Birbhum Division | PARULIA PIPED WATER SUPPLY SCHEME. | SM/14538 | New | Different works related to water supply scheme at PARULIA, KHANPUR & PADUMA and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE,JE3 | ORD/000076/2023-2024 | 1425/BHM | 25/04/2023 | 01/01/2026 | BIPIN KUMAR SINGH | 2248.63 | 0 | 0 | 55
4 | BIRBHUM | Dubrajpur | Birbhum Division | PARULIA PIPED WATER SUPPLY SCHEME. | SM/14538 | New | Laying of distribution system and road restoration at Parulia Piped Water Supply Scheme, Dubrajpur Block, under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE | JE3 | ORD/000271/2025-2026 | 2417/BHM | 18/09/2025 | 17/12/2025 | BIPIN KUMAR SINGH | 68.09 | 0 | 0 | 0
Total | [13 empty] | 2580.09 | 0 | 0