## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Paduma Piped Water Supply Scheme. | SM/14544 | New | Providing Electro-mechanical accessories and others for Paduma PWSS at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000397/2023-2024 | 2075/BOL.MD. | 21/08/2023 | 19/11/2023 | S.P. CONSTRUCTION | 80.24 | 37.11 | 46.25 | 40
2 | BIRBHUM | Dubrajpur | Birbhum Division | Paduma Piped Water Supply Scheme. | SM/14544 | New | Different works related to water supply scheme at PARULIA, KHANPUR & PADUMA and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE,JE3 | ORD/000076/2023-2024 | 1425/BHM | 25/04/2023 | 30/06/2026 | BIPIN KUMAR SINGH | 2248.63 | 60.89 | 2.71 | 55
Total | [13 empty] | 2328.87 | 98 | 4.21