## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 1518/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 36.07 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Duna PWSS under Mayureswar - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001236/2023-2024 | 521/BOL.MD | 14/03/2024 | 13/05/2024 | PRADIP KUMAR DHABAL | 7.62 | 0 | 0 | 0
3 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Supply, Delivewry and storage of vacuum operated gaseous Chlorination system for Duna PWSS, Block : Mayureswar-II under Bolpur Mechanical Division.PHE.DTE. | Assistant Engineer-III | Junior Engineer | ORD/000515/2024-2025 | 3761/Bol.MD | 12/09/2024 | 12/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 28.84 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar-II | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Continuation Work Order for Preparation & Submission of DPR for (DUNA) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE | JE3 | ORD/000839/2022-2023 | 423/RSD | 03/11/2022 | 18/12/2022 | ENVIROTECH SOLUTIONS | 2.86 | 2.51 | 87.71 | 100
5 | BIRBHUM | Mayureswar-II | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Continuation Work Order for Preparation & Submission of DPR for (DUNA) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE | JE3 | ORD/000838/2022-2023 | 296/RSD | 07/09/2022 | 22/10/2022 | ENVIROTECH SOLUTIONS | 3.22 | 2.34 | 72.75 | 100
6 | BIRBHUM | Mayureswar-II | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Material Requisition To Resource Division |  |  | RTOR000210/2023-2024 | 208/BHM | 22/01/2024 | 22/01/2024 | Resource Division | 1.54 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar-II | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Different works related to Water Supply Scheme at DUNA & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000057/2023-2024 | 1249/BHM | 17/04/2023 | 01/07/2025 | CREATIVE CONSTRUCTION | 473.21 | 34.1 | 7.21 | 50
8 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Providing Electro-mechanical accessories and others for Duna PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000842/2023-2024 | 3281/BOL.MD | 29/09/2023 | 31/08/2025 | DEY ENTERPRISE | 55.7 | 0 | 0 | 61
Total | [13 empty] | 609.06 | 38.95 | 6.4