## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 1518/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 36.07 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Duna PWSS under Mayureswar - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001236/2023-2024 | 521/BOL.MD | 14/03/2024 | 13/05/2024 | PRADIP KUMAR DHABAL | 7.62 | 0 | 0 | 0
3 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Supply, Delivewry and storage of vacuum operated gaseous Chlorination system for Duna PWSS, Block : Mayureswar-II under Bolpur Mechanical Division.PHE.DTE. | Assistant Engineer-III | Junior Engineer | ORD/000515/2024-2025 | 3761/Bol.MD | 12/09/2024 | 12/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 28.84 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar-II | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Continuation Work Order for Preparation & Submission of DPR for (DUNA) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE | JE3 | ORD/000839/2022-2023 | 423/RSD | 03/11/2022 | 18/12/2022 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 0 | 100
5 | BIRBHUM | Mayureswar-II | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Continuation Work Order for Preparation & Submission of DPR for (DUNA) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE | JE3 | ORD/000838/2022-2023 | 296/RSD | 07/09/2022 | 22/10/2022 | ENVIROTECH SOLUTIONS | 3.22 | 0 | 0 | 100
6 | BIRBHUM | Mayureswar-II | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Material Requisition To Resource Division |  |  | RTOR000210/2023-2024 | 208/BHM | 22/01/2024 | 22/01/2024 | Resource Division | 1.54 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar-II | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Different works related to Water Supply Scheme at DUNA & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000057/2023-2024 | 1249/BHM | 17/04/2023 | 01/07/2025 | CREATIVE CONSTRUCTION | 473.21 | 0 | 0 | 50
8 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Providing Electro-mechanical accessories and others for Duna PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000842/2023-2024 | 3281/BOL.MD | 29/09/2023 | 31/08/2025 | DEY ENTERPRISE | 55.7 | 0 | 0 | 61
9 | BIRBHUM | Mayureswar-II | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14675 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE | Estimator,JE | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 16/04/2025 | IMAGIN | 67.84 | 0 | 0 | 100
Total | [13 empty] | 676.9 | 0 | 0