## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar-II | Birbhum Division | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14676 | New | Continuation Work Order for Preparation & Submission of DPR for (Khagra) Water Supply Scheme under Mayureswar-II Development Block. | AE | JE3 | ORD/000564/2022-2023 | 186/RSD | 10/05/2022 | 24/06/2022 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 0 | 100
2 | BIRBHUM | Mayureswar-II | Birbhum Division | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14676 | New | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 1536/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 10.76 | 0 | 0 | 0
3 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14676 | New | Supply & delivery of submersible Pumping Machineries & cable at Khagra Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000605/2024-2025 | 1455./AE-III | 09/09/2024 | 16/09/2024 | PRADIP KUMAR DHABAL | 2.83 | 0 | 0 | 100
4 | BIRBHUM | Mayureswar-II | Birbhum Division | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14676 | New | Material Requisition To Resource Division |  |  | RTOR000211/2023-2024 | 201/BHM | 22/01/2024 | 22/01/2024 | Resource Division | 2.03 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14676 | New | New Power connection at Khagra PWSS (P/H-I) under Mayureswar-II Block |  |  | BILL/00129/2024-2025 | BP-2024-2025-56 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.9 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14676 | New | New Power connection at Khagra (PH-II) PWSS, under Bolpur Mechanical Division, P.H.e.Dte. |  |  | BILL/00075/2024-2025 | BP-2024-2025-27 | 20/05/2024 | 20/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.88 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar-II | Birbhum Division | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14676 | New | Different works related to Water Supply Scheme at KHAGRA & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000158/2023-2024 | 2066/BHM | 08/06/2023 | 01/01/2026 | MALLICK CONSTRUCTION | 243.5 | 0 | 0 | 65
8 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14676 | New | Providing Electro-mechanical accessories and others for Khagra PWSS at Mayurreswar - II Block under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000841/2023-2024 | 3280/BOL.MD | 29/09/2023 | 01/06/2025 | QUAZI NOZRUL ISLAM | 44.01 | 0 | 0 | 40
9 | BIRBHUM | Mayureswar-II | Bolpur Mechanical | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT | SM/14676 | New | Supply & delivery of different electrical accessories at Khagra Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000449/2024-2025 | 1300./AE-III | 27/08/2024 | 03/09/2024 | QUAZI NOZRUL ISLAM | 2.96 | 0 | 0 | 100
Total | [13 empty] | 318.73 | 0 | 0