## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | KHAYERBANI PIPED WATER SUPPLY SCHEME | SM/14677 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for KHAYERBANI Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | AE | JE3 | ORD/000656/2022-2023 | 163/BSD | 25/04/2022 | 22/10/2022 | APEX ENGINEERING | 3.16 | 2.53 | 80.02 | 100
2 | BIRBHUM | Labpur | Central Drilling | KHAYERBANI PIPED WATER SUPPLY SCHEME | SM/14677 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | BIRBHUM | Labpur | Birbhum Division | KHAYERBANI PIPED WATER SUPPLY SCHEME | SM/14677 | New | Material Requisition To Resource Division |  |  | RTOR000159/2023-2024 | 1599/BHM | 27/04/2023 | 27/04/2023 | Resource Division | 19.67 | 0 | 0 | 0
4 | BIRBHUM | Labpur | Birbhum Division | KHAYERBANI PIPED WATER SUPPLY SCHEME | SM/14677 | New | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,JE1,JE3 | ORD/000084/2024-2025 | 1948/BHM | 04/07/2024 | 04/07/2027 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0 | 0
5 | BIRBHUM | Labpur | Birbhum Division | KHAYERBANI PIPED WATER SUPPLY SCHEME | SM/14677 | New | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 2387/BHM | 27/08/2024 | 27/08/2024 | Resource Division | 7.2 | 0 | 0 | 0
6 | BIRBHUM | Labpur | Bolpur Mechanical | KHAYERBANI PIPED WATER SUPPLY SCHEME | SM/14677 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Khayerbani PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer (HQ) | Junior Engineer | ORD/001127/2024-2025 | 330/BOL.MD | 19/02/2025 | 19/06/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 74.48 | 0 | 0 | 0
Total | [13 empty] | 23459.02 | 2.53 | 0.01