## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | SAJNOR PIPED WATER SUPPLY SCHEME | SM/14678 | New | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 1456/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 16.14 | 0 | 0 | 0
2 | BIRBHUM | Nanoor | Birbhum Division | SAJNOR PIPED WATER SUPPLY SCHEME | SM/14678 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for SAJNOR Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | AE | JE4 | ORD/000740/2022-2023 | 279/BSD | 21/07/2022 | 19/10/2022 | RADIANT | 4.94 | 0 | 0 | 100
3 | BIRBHUM | Nanoor | Birbhum Division | SAJNOR PIPED WATER SUPPLY SCHEME | SM/14678 | New | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 2394/BHM | 27/08/2024 | 27/08/2024 | Resource Division | 12.08 | 0 | 0 | 0
4 | BIRBHUM | Nanoor | Central Drilling | SAJNOR PIPED WATER SUPPLY SCHEME | SM/14678 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | BIRBHUM | Nanoor | Birbhum Division | SAJNOR PIPED WATER SUPPLY SCHEME | SM/14678 | New | Construction of 250 & 150 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main, Distribution System with FHTC including different works related to SANTOSHPUR / NAWADA PALANDI /PAPURI / SAJNOR / RAYEN PIPED WATER SUPPLY SCHEME (5 Nos Scheme) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division PHE DTE. | AE | JE2,Bolpur Sub-Division,JE3 | ORD/000085/2024-2025 | 1951/BHM | 04/07/2024 | 04/07/2026 | UMWELT ENGINEER PVT. LTD. | 2322.64 | 0 | 0 | 5
Total | [13 empty] | 23695.57 | 0 | 0