## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-II | Birbhum Division | Hazaripur Piped Water Supply Scheme | SM/14679 | New | Preparation and submission of DPR for (Hazaripur) Water Supply Scheme under Nalhati-II Development Block. | AE | JE2 | ORD/000757/2022-2023 | 222/AE/NSD | 18/04/2022 | 02/06/2022 | MS SOBHA AND CO | 4.71 | 4.71 | 100 | 100
2 | BIRBHUM | Nalhati-II | Birbhum Division | Hazaripur Piped Water Supply Scheme | SM/14679 | New | Material Requisition To Resource Division |  |  | RTOR000173/2023-2024 | 2173/BHM | 23/06/2023 | 23/06/2023 | Resource Division | 25.03 | 0 | 0 | 0
3 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Hazaripur Piped Water Supply Scheme | SM/14679 | New | Supply and Delivery of Electro mechanical Accessories for Hazaripur PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000519/2024-2025 | 3779/BOL.MD | 12/09/2024 | 12/10/2024 | KAMAKHYA ENTERPRISE | 28.62 | 28.62 | 100 | 100
4 | BIRBHUM | Nalhati-II | Birbhum Division | Hazaripur Piped Water Supply Scheme | SM/14679 | New | Different works for works related to water supply scheme at HAZARIPUR, Beloa & its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000255/2023-2024 | 3425/BHM | 02/08/2023 | 01/01/2026 | M/S NATIONAL CONSTRUCTION | 1099.34 | 11.33 | 1.03 | 15
5 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Hazaripur Piped Water Supply Scheme | SM/14679 | New | Providing Electro-mechanical accessories and others for Hazaripur PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000462/2023-2024 | 2136/Bol.MD | 25/08/2023 | 01/03/2025 | SINHA ELECTRICALS | 45.52 | 18.35 | 40.32 | 30
6 | BIRBHUM | Nalhati-II | Birbhum Division | Hazaripur Piped Water Supply Scheme | SM/14679 | New | Restoration of Roads, pucca drain including Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Hazaripur piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | AE | JE2 | ORD/000166/2025-2026 | 2064/BHM | 12/08/2025 | 10/11/2025 | M/S NATIONAL CONSTRUCTION | 61.62 | 0 | 0 | 0
7 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Hazaripur Piped Water Supply Scheme | SM/14679 | New | Quotation for new service connection at Hazaripur PWSS Head work site (mouza- Simlandi) at Nalhati-II |  |  | BILL/01787/2024-2025 |  | 24/03/2025 | 24/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.26 | 0 | 0 | 0
8 | BIRBHUM | Nalhati-II | Bolpur Mechanical | Hazaripur Piped Water Supply Scheme | SM/14679 | New | Quotation for new service connection at Hazaripur PWSS P/H- II (Mouza- Simlandi) at Block- Nalhati-II |  |  | BILL/01124/2024-2025 | BP-24-25-296 | 10/01/2025 | 10/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.85 | 0 | 0 | 0
Total | [13 empty] | 1273.95 | 63.01 | 4.95