## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Sekedda Piped Water Supply Scheme. | SM/14683 | New | Supply & Installation of Low lift Pumping Mchinery and other allied work for SEKADDAHA & Adjoining moujas water supply scheme within Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000549/2023-2024 | 2145/Bol.MD | 25/08/2023 | 23/11/2023 | WEST BENGAL ENGINEERING CO. | 75.81 | 0 | 0 | 0
2 | BIRBHUM | Mohammad Bazar | Birbhum Division | Sekedda Piped Water Supply Scheme. | SM/14683 | New | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 1497/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 484.43 | 0 | 0 | 0
3 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Sekedda Piped Water Supply Scheme. | SM/14683 | New | Supply & Installation of High lift Pumping Mchinery and other allied work for SEKADDAHA & Adjoining moujas water supply scheme within Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer,Driller in Charge | Junior Engineer | ORD/000552/2023-2024 | 2148/Bol.MD | 25/08/2023 | 23/11/2023 | ORIENTAL ENGINEERING CO. | 92.33 | 0 | 0 | 10
4 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Sekedda Piped Water Supply Scheme. | SM/14683 | New | Providing Electro-mechanical accessories and others for Sekedda PWSS (New Tube Well) at Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/001192/2023-2024 | 367/BOL.MD | 06/03/2024 | 05/04/2024 | HINDOL ROY | 13.96 | 10.38 | 74.35 | 100
5 | BIRBHUM | Mohammad Bazar | Birbhum Division | Sekedda Piped Water Supply Scheme. | SM/14683 | New | Different works related to water supply scheme at SEKEDDAHA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ) | Estimator,JE,JE1 | ORD/000109/2024-2025 | 2139/BHM | 31/07/2024 | 31/07/2025 | M/S GOUTAM DAS | 1425.93 | 0 | 0 | 25
Total | [13 empty] | 2092.45 | 10.38 | 0.5