## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Ruppur and adjoining mouzas Piped Water Supply Scheme. | SM/14686 | New | Material Requisition To Resource Division |  |  | RTOR000092/2022-2023 | 1363/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 263.55 | 0 | 0 | 0
2 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Ruppur and adjoining mouzas Piped Water Supply Scheme. | SM/14686 | New | Providing Electro-mechanical accessories and others for Ruppur & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000876/2023-2024 | 3514/Bol.MD | 24/11/2023 | 22/02/2024 | M. S. ENTERPRISE | 88.27 | 58.84 | 66.66 | 85
Total | [13 empty] | 351.82 | 58.84 | 16.72