## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Ruppur and adjoining mouzas Piped Water Supply Scheme. | SM/14686 | New | Material Requisition To Resource Division |  |  | RTOR000092/2022-2023 | 1363/BHM | 24/04/2023 | 24/04/2023 | Resource Division | 263.55 | 0 | 0 | 0
2 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Ruppur and adjoining mouzas Piped Water Supply Scheme. | SM/14686 | New | Providing Electro-mechanical accessories and others for Ruppur & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000876/2023-2024 | 3514/Bol.MD | 24/11/2023 | 22/02/2024 | M. S. ENTERPRISE | 88.27 | 58.84 | 66.66 | 85
3 | BIRBHUM | Bolpur Sriniketan | Central Drilling | Ruppur and adjoining mouzas Piped Water Supply Scheme. | SM/14686 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
4 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Ruppur and adjoining mouzas Piped Water Supply Scheme. | SM/14686 | New | Different works related to water supply scheme at MONOHARPUR, MOSTALA, RUPPUR & SALAN Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE4,JE_BLK_NANOOR | ORD/000398/2023-2024 | 4137/BHM | 18/10/2023 | 09/01/2026 | NAUTANDAS AND CO | 2897.79 | 0 | 0 | 10
Total | [13 empty] | 24589.38 | 58.84 | 0.24