## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati-I | Birbhum Division | Banior Piped Water Supply Scheme. | SM/14688 | New | Different works related to water supply scheme at BANIOR & its adjoining mouzas water supply scheme within NALHATI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000332/2023-2024 | 3777/BHM | 08/09/2023 | 01/09/2025 | TUSHAR KANTI GHOSH | 1573.21 | 50.74 | 3.23 | 12
2 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Banior Piped Water Supply Scheme. | SM/14688 | New | Supply & Installation of Low lift pumping machineries and other allied works for Banior piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000930/2023-2024 | 3560/BOL.MD | 04/12/2023 | 02/04/2025 | QUAZI NOZRUL ISLAM | 74.52 | 58.18 | 78.07 | 30
3 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Banior Piped Water Supply Scheme. | SM/14688 | New | Supply & Installation of High lift pumping machineries and other allied works for Banior piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte.. | Assistant Engineer-III | Junior Engineer | ORD/000919/2023-2024 | 3557/BOL.MD | 04/12/2023 | 01/10/2024 | MACHINE SUPPLIERS SYNDUCATE (P) LTD. | 95.52 | 66.34 | 69.46 | 40
4 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Banior Piped Water Supply Scheme. | SM/14688 | New | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/001441/2023-2024 | 3317/BOL.MD | 29/09/2023 | 28/01/2024 | SATYAJIT GHOSH | 0.57 | 1.53 | 265.63 | 100
5 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Banior Piped Water Supply Scheme. | SM/14688 | New | Hiring of Luxury car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/001443/2023-2024 | 1221/BOL.MD. | 26/06/2023 | 27/10/2023 | RAJIB GHOSH | 0.58 | 0.39 | 67.32 | 0
6 | BIRBHUM | Nalhati-I | Birbhum Division | Banior Piped Water Supply Scheme. | SM/14688 | New | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 1625/BHM | 28/04/2023 | 28/04/2023 | Resource Division | 654.06 | 0 | 0 | 0
7 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Banior Piped Water Supply Scheme. | SM/14688 | New | Hiring of Luxury Car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/001444/2023-2024 | 205/Bol.MD | 27/02/2024 | 27/06/2024 | RAJIB GHOSH | 0.57 | 1.56 | 271.5 | 0
8 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Banior Piped Water Supply Scheme. | SM/14688 | New | Hiring of Luxury Car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/000643/2024-2025 | 1675/BOL.MD | 28/06/2024 | 27/10/2024 | RAJIB GHOSH | 0.57 | 1.52 | 264.38 | 100
9 | BIRBHUM | Nalhati-I | Bolpur Mechanical | Banior Piped Water Supply Scheme. | SM/14688 | New | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/001442/2023-2024 | 174/BOL.MD | 21/02/2024 | 21/06/2024 | SATYAJIT GHOSH | 0.57 | 1.54 | 267.1 | 0
Total | [13 empty] | 2400.19 | 181.8 | 7.57