## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | PAPURI PIPED WATER SUPPLY SCHEME | SM/14691 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 1467/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 36.41 | 0 | 0 | 0
2 | BIRBHUM | Nanoor | Birbhum Division | PAPURI PIPED WATER SUPPLY SCHEME | SM/14691 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for PAPURI Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | AE | JE4 | ORD/000739/2022-2023 | 269/BSD | 15/07/2022 | 13/10/2022 | RADIANT | 4.94 | 4.76 | 96.29 | 100
3 | BIRBHUM | Nanoor | Birbhum Division | PAPURI PIPED WATER SUPPLY SCHEME | SM/14691 | New | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 2393/BHM | 27/08/2024 | 27/08/2024 | Resource Division | 12.11 | 0 | 0 | 0
4 | BIRBHUM | Nanoor | Birbhum Division | PAPURI PIPED WATER SUPPLY SCHEME | SM/14691 | New | Construction of 250 & 150 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main, Distribution System with FHTC including different works related to SANTOSHPUR / NAWADA PALANDI /PAPURI / SAJNOR / RAYEN PIPED WATER SUPPLY SCHEME (5 Nos Scheme) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division PHE DTE. | AE | JE2,Bolpur Sub-Division,JE3 | ORD/000085/2024-2025 | 1951/BHM | 04/07/2024 | 04/07/2026 | UMWELT ENGINEER PVT. LTD. | 2322.64 | 0 | 0 | 5
5 | BIRBHUM | Nanoor | Bolpur Mechanical | PAPURI PIPED WATER SUPPLY SCHEME | SM/14691 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Papuri Water supply Scheme (T/W-I & II), Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000965/2024-2025 | 4534/BOL.MD | 20/12/2024 | 19/04/2025 | PADMA ENGINEERING CO. | 73.34 | 0 | 0 | 45
6 | BIRBHUM | Nanoor | Bolpur Mechanical | PAPURI PIPED WATER SUPPLY SCHEME | SM/14691 | New | SHIFTING OF 11KV OH HAT SERANDI FEEDER (AT PAPURI) EMANATED FROM PANSWA 33/11 KV SUB-STATION UNDER BOLPUR MECHANICAL DIVISION PHE Dte. |  |  | BILL/00317/2025-2026 | 115/08 | 30/07/2025 | 30/07/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.48 | 0 | 0 | 0
7 | BIRBHUM | Nanoor | Central Drilling | PAPURI PIPED WATER SUPPLY SCHEME | SM/14691 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 23792.7 | 4.76 | 0.02