## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | KURUMBA PIPED WATER SUPPLY SCHEME | SM/14743 | New | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 1566/BHM | 26/04/2023 |  | Resource Division | 27.55 | 0 | 0 | 0
2 | BIRBHUM | Labpur | Birbhum Division | KURUMBA PIPED WATER SUPPLY SCHEME | SM/14743 | New | Material Requisition To Resource Division |  |  | RTOR000157/2023-2024 | 1600/BHM | 27/04/2023 |  | Resource Division | 27.55 | 0 | 0 | 0
3 | BIRBHUM | Labpur | Birbhum Division | KURUMBA PIPED WATER SUPPLY SCHEME | SM/14743 | New | Different works related to water supply scheme at KURUMBA PIPED WATER SUPPLY SCHEME (TSM016231) within LABPUR Block including supply of all Labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000568/2022-2023 | 901/BHM | 22/03/2023 | 17/12/2023 | ESCON INDIA | 440.1 | 0 | 0 | 0
4 | BIRBHUM | Labpur | Birbhum Division | KURUMBA PIPED WATER SUPPLY SCHEME | SM/14743 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for KURUMBA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | AE | JE3 | ORD/001144/2021-2022 | 112/BSD | 25/03/2022 | 21/09/2022 | APEX ENGINEERING | 3.87 | 1.7 | 43.91 | 100
5 | BIRBHUM | Labpur | Central Drilling | KURUMBA PIPED WATER SUPPLY SCHEME | SM/14743 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21838.82 | 1.7 | 0.01