## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2022-2023 | 972/BHM | 27/03/2023 |  | Resource Division | 102.97 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1125/BHM | 10/04/2023 |  | Resource Division | 14.94 | 0 | 0 | 0
3 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Supply,delivery and Installation of PDB cum MCC Panel and allieds works at Mayureswar water supply scheme ( under Augmentation of Narayanpur Piped Water Supply Scheme, Block-Rampurhat-II) under Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/000488/2023-2024 | 2243/BOL.MD. | 13/09/2023 | 12/11/2023 | UTTAM KUMAR CHATTERJEE | 15.71 | 14.35 | 91.35 | 80
4 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Supply and Delivery of Sub-Mersible Pumping Machineries for Ground Based Tube Well for Narayanpur water supply scheme (Block- Rampurhat - I) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001041/2023-2024 | 1622/AE-III | 18/12/2023 | 08/01/2024 | M/S. YOUTH ENGINEERS' ENTERPRISE | 1.87 | 0.94 | 50.45 | 100
5 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Wells and allieds works at Augmentation of Narayanpur water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001211/2023-2024 | 373/BOL.MD | 06/03/2024 | 05/04/2024 | QUAZI NOZRUL ISLAM | 13.39 | 12.43 | 92.83 | 0
6 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Supply and installation of Submersible pumping Machineries and HL Pumping Machineries with allied works at Augmentation of Narayanpur (Zone - II) PWSS, Block-Rampurhat- II under Bolpur Mechanical Division PHED. | Assistant Engineer-III | Junior Engineer | ORD/000529/2023-2024 | 2117/Bol.MD | 23/08/2023 | 21/11/2023 | SINHA ELECTRICALS | 98.04 | 64.01 | 65.29 | 30
7 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well at Augmentation of Narayanpur (Zone-II) PWSS, (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001215/2023-2024 | 400/Bol.MD | 07/03/2024 | 21/04/2024 | SINHA ELECTRICALS | 79.02 | 63.99 | 80.98 | 30
8 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Supply and Delivery of Voltage Correction Devices for Augmentation of Narayanpur (Zone-II) PWSS, (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000514/2024-2025 | 3778/BOL.MD | 12/09/2024 | 12/10/2024 | SINHA ELECTRICALS | 41.51 | 26.97 | 64.97 | 0
Total | [13 empty] | 367.44 | 182.69 | 49.72