## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1125/BHM | 10/04/2023 | 10/04/2023 | Resource Division | 14.94 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2022-2023 | 972/BHM | 27/03/2023 | 27/03/2023 | Resource Division | 102.97 | 0 | 0 | 0
3 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Supply and installation of Submersible pumping Machineries and HL Pumping Machineries with allied works at Augmentation of Narayanpur (Zone - II) PWSS, Block-Rampurhat- II under Bolpur Mechanical Division PHED. | Assistant Engineer-III | Junior Engineer | ORD/000529/2023-2024 | 2117/Bol.MD | 23/08/2023 | 01/06/2025 | SINHA ELECTRICALS | 98.04 | 0 | 0 | 30
4 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Wells and allieds works at Augmentation of Narayanpur water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001211/2023-2024 | 373/BOL.MD | 06/03/2024 | 05/04/2024 | QUAZI NOZRUL ISLAM | 13.39 | 0 | 0 | 70
5 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Supply and Delivery of Sub-Mersible Pumping Machineries for Ground Based Tube Well for Narayanpur water supply scheme (Block- Rampurhat - I) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001041/2023-2024 | 1622/AE-III | 18/12/2023 | 08/01/2024 | M/S. YOUTH ENGINEERS' ENTERPRISE | 1.87 | 0 | 0 | 100
6 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Supply and Delivery of Voltage Correction Devices for Augmentation of Narayanpur (Zone-II) PWSS, (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000514/2024-2025 | 3778/BOL.MD | 12/09/2024 | 12/10/2024 | SINHA ELECTRICALS | 41.51 | 0 | 0 | 100
7 | BIRBHUM |  | Birbhum Division | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at NARAYANPUR (Zone-I & Zone-II) & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materialsunder BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000190/2024-2025 | 2769/BHM | 30/09/2024 | 30/09/2026 | M/S GHOSH AND CO. | 518.25 | 0 | 0 | 20
8 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. | SM/14744 | Augmentation | Supply,delivery and Installation of PDB cum MCC Panel and allieds works at Mayureswar water supply scheme ( under Augmentation of Narayanpur Piped Water Supply Scheme, Block-Rampurhat-II) under Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/000488/2023-2024 | 2243/BOL.MD. | 13/09/2023 | 01/04/2025 | UTTAM KUMAR CHATTERJEE | 15.71 | 0 | 0 | 100
Total | [13 empty] | 806.67 | 0 | 0