## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | DULA SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14746 | New | Material Requisition To Resource Division |  |  | RTOR000147/2023-2024 | 1598/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 23.88 | 0 | 0 | 0
2 | BIRBHUM | Labpur | Birbhum Division | DULA SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14746 | New | Different works related to water supply scheme at DULA SAHAPUR PIPED WATER SUPPLY SCHEME (TSM017017) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE3 | ORD/000303/2024-2025 | 3022/BHM | 30/10/2024 | 30/10/2025 | M/S S. CHOUDHURY | 597.84 | 0 | 0 | 0
3 | BIRBHUM | Labpur | Birbhum Division | DULA SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14746 | New | Continuation work for "Preparation & Submission of additional Detail Project Report (DPR) for DULASAHAPARA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE3 | ORD/000952/2022-2023 | 293/BSD | 29/07/2022 | 27/10/2022 | APEX ENGINEERING | 1.41 | 0 | 0 | 100
4 | BIRBHUM | Labpur | Birbhum Division | DULA SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14746 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for DULASAHAPARA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE3 | ORD/000947/2022-2023 | 232/BSD | 10/06/2022 | 07/12/2022 | APEX ENGINEERING | 4.92 | 0 | 0 | 100
5 | BIRBHUM | Labpur | Central Drilling | DULA SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14746 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | BIRBHUM | Labpur | Bolpur Mechanical | DULA SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14746 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Dula Sahapur PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer (HQ) | Junior Engineer | ORD/001118/2024-2025 | 326/BOL.MD | 19/02/2025 | 19/06/2025 | SUNRISE ENGINEERING CORPORATION | 74.48 | 0 | 0 | 0
Total | [13 empty] | 22042.29 | 0 | 0