## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-I | Birbhum Division | Kanduri Piped Water Supply Scheme. | SM/14824 | New | Material Requisition To Resource Division |  |  | RTOR000142/2023-2024 | 1577/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 9.64 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-I | Birbhum Division | Kanduri Piped Water Supply Scheme. | SM/14824 | New | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | 2452/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 12.18 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat-I | Birbhum Division | Kanduri Piped Water Supply Scheme. | SM/14824 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 200 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to KANDURI & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE2,JE3 | ORD/000097/2024-2025 | 2110/BHM | 29/07/2024 | 01/04/2026 | PULAK KUMAR PAL | 409.54 | 25 | 6.1 | 35
4 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Kanduri Piped Water Supply Scheme. | SM/14824 | New | Quotation for new service connection at Kanduri PWSS P/H-I at Block- Rampurhat-I |  |  | BILL/01243/2024-2025 | BP-24-25-361 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.85 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Kanduri Piped Water Supply Scheme. | SM/14824 | New | Quotation for new service connection at Kanduri PWSS P/H-2 , Block- Rampurhat-I |  |  | BILL/01244/2024-2025 | BP-24-25-360 | 27/03/2025 | 27/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat-I | Bolpur Mechanical | Kanduri Piped Water Supply Scheme. | SM/14824 | New | Providing Electro-mechanical accessories and others for Kanduri & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000918/2023-2024 | 3526/Bol.MD | 29/11/2023 | 01/12/2025 | ORIENTAL ENGINEERING CO. | 27.48 | 0 | 0 | 50
Total | [13 empty] | 466.69 | 25 | 5.36