## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | BALIARA PIPED WATER SUPPLY SCHEME | SM/14847 | New | Different works related to water supply scheme at BALIARA & its adjoining mouzas water supply scheme within NANOOR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE4 | ORD/000077/2023-2024 | 1426/BHM | 25/04/2023 | 25/01/2024 | M/S REBATI SANKAR SINHA | 378.55 | 0 | 0 | 0
2 | BIRBHUM | Nanoor | Birbhum Division | BALIARA PIPED WATER SUPPLY SCHEME | SM/14847 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BALIARA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE4 | ORD/001134/2021-2022 | 103/BSD | 16/03/2022 | 14/06/2022 | RADIANT | 4.36 | 4.19 | 96.06 | 100
3 | BIRBHUM | Nanoor | Birbhum Division | BALIARA PIPED WATER SUPPLY SCHEME | SM/14847 | New | Material Requisition To Resource Division |  |  | RTOR000133/2023-2024 | 1559/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 22.71 | 0 | 0 | 0
4 | BIRBHUM | Nanoor | Bolpur Mechanical | BALIARA PIPED WATER SUPPLY SCHEME | SM/14847 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Baliara WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000962/2024-2025 | 4531/BOL.MD | 20/12/2024 | 19/04/2025 | SATYAJIT GHOSH | 75.08 | 0 | 0 | 0
Total | [13 empty] | 480.7 | 4.19 | 0.87