## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | BHETER PIPED WATER SUPPLY SCHEME | SM/14848 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHETER Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE4 | ORD/000620/2022-2023 | 132/BSD | 05/04/2022 | 04/07/2022 | RADIANT | 3.27 | 0 | 0 | 100
2 | BIRBHUM | Nanoor | Birbhum Division | BHETER PIPED WATER SUPPLY SCHEME | SM/14848 | New | Material Requisition To Resource Division |  |  | RTOR000136/2023-2024 | 1553/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 27.28 | 0 | 0 | 0
3 | BIRBHUM | Nanoor | Birbhum Division | BHETER PIPED WATER SUPPLY SCHEME | SM/14848 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 150 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to Piped Water supply scheme at Bheter & its adjoining mouzas within NANOOR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | Assistant Engineer | JE_BLK_NANOOR | ORD/000112/2024-2025 | 2164/BHM | 05/08/2024 | 05/08/2025 | PALCON | 301.86 | 0 | 0 | 0
4 | BIRBHUM | Nanoor | Birbhum Division | BHETER PIPED WATER SUPPLY SCHEME | SM/14848 | New | Material Requisition To Resource Division |  |  | RTOR000023/2024-2025 | 2446/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 6.97 | 0 | 0 | 0
5 | BIRBHUM | Nanoor | Central Drilling | BHETER PIPED WATER SUPPLY SCHEME | SM/14848 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | BIRBHUM | Nanoor | Bolpur Mechanical | BHETER PIPED WATER SUPPLY SCHEME | SM/14848 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Bheter WSS (TW No. I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000955/2024-2025 | 4522/BOL.MD | 20/12/2024 | 01/01/2026 | SATYAJIT GHOSH | 75.08 | 0 | 0 | 50
Total | [13 empty] | 21754.22 | 0 | 0