## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | RANIBAZAR PIPED WATER SUPPLY SCHEME | SM/14850 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for RANIBAZAR Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE4 | ORD/000647/2022-2023 | 187/BSD | 11/05/2022 | 09/08/2022 | RADIANT | 4 | 3.89 | 97.35 | 100
2 | BIRBHUM | Nanoor | Birbhum Division | RANIBAZAR PIPED WATER SUPPLY SCHEME | SM/14850 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1514/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 14.12 | 0 | 0 | 0
3 | BIRBHUM | Nanoor | Birbhum Division | RANIBAZAR PIPED WATER SUPPLY SCHEME | SM/14850 | New | Construction of 200 CuM capacity O.H.R.with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements,laying of Rising Main,Distribution System with FHTC and different works related to RANIBAZAR PIPED WATER SUPPLY SCHEME (TSM/017432) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE2 | ORD/000160/2024-2025 | 2664/BHM | 13/09/2024 | 13/09/2025 | PATHIK PABAN NANDI | 417.11 | 0 | 0 | 0
4 | BIRBHUM | Nanoor | Bolpur Mechanical | RANIBAZAR PIPED WATER SUPPLY SCHEME | SM/14850 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Ranibazar WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | Assistant Engineer | Junior Engineer | ORD/000958/2024-2025 | 4527/BOL.MD | 20/12/2024 | 19/04/2025 | SATYAJIT GHOSH | 75.08 | 0 | 0 | 50
Total | [13 empty] | 510.31 | 3.89 | 0.76