## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Khoyrasol | Birbhum Division | Palashbuni Piped Water Supply Scheme (Khoyrasole Block) | SM/14851 | New | Preparation & Submission of DPR for Palashbuni & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000681/2022-2023 | 134/BSSD | 18/07/2022 | 01/09/2022 | RADIANT | 2.72 | 2.72 | 100 | 100
2 | BIRBHUM | Khoyrasol | Birbhum Division | Palashbuni Piped Water Supply Scheme (Khoyrasole Block) | SM/14851 | New | Material Requisition To Resource Division |  |  | RTOR000245/2023-2024 | 425/BHM | 01/02/2024 | 01/02/2024 | Resource Division | 131.6 | 0 | 0 | 0
Total | [13 empty] | 134.32 | 2.72 | 2.03