## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Khoyrasol | Birbhum Division | Haripur Piped Water Supply Scheme | SM/14853 | New | Preparation & Submission of DPR for Pump House cum Chlorine Room, Boundary Wall, Soil Investigation Report, Construction Over Head Reservoir (OHR), Construction of Pipe carrying structure, Service Road at Head Work Site & Land Development, FHTC Connection of Haripur & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000859/2022-2023 | 93/BSSD | 27/05/2022 | 11/07/2022 | RADIANT | 2.22 | 2.22 | 100 | 100
2 | BIRBHUM | Khoyrasol | Birbhum Division | Haripur Piped Water Supply Scheme | SM/14853 | New | Preparation & Submission of DPR for laying distribution of Haripur & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000858/2022-2023 | 88/BSSD | 20/05/2022 | 04/07/2022 | RADIANT | 3.18 | 3.18 | 100 | 100
3 | BIRBHUM | Khoyrasol | Birbhum Division | Haripur Piped Water Supply Scheme | SM/14853 | New | Material Requisition To Resource Division |  |  | RTOR000241/2023-2024 | 427/BHM | 01/02/2024 | 01/02/2024 | Resource Division | 328.76 | 0 | 0 | 0
Total | [13 empty] | 334.15 | 5.4 | 1.62