## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Khoyrasol | Birbhum Division | Noapara Piped Water Supply Scheme (Khoyrasole G.P.) | SM/14854 | New | Preparation & Submission of DPR for Noapara & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000672/2022-2023 | 86/BSSD | 19/05/2022 | 03/07/2022 | RADIANT | 3.33 | 3.33 | 100 | 100
2 | BIRBHUM | Khoyrasol | Birbhum Division | Noapara Piped Water Supply Scheme (Khoyrasole G.P.) | SM/14854 | New | Material Requisition To Resource Division |  |  | RTOR000244/2023-2024 | 432/BHM | 01/02/2024 | 01/02/2024 | Resource Division | 142.08 | 0 | 0 | 0
Total | [13 empty] | 145.41 | 3.33 | 2.29