## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Khoyrasol | Birbhum Division | Parsundi Piped Water Supply Scheme | SM/14855 | New | Preparation & Submission of DPR for Parsundi & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000855/2022-2023 | 143/BSSD | 21/07/2022 | 04/09/2022 | RADIANT | 2.9 | 0 | 0 | 100
2 | BIRBHUM | Khoyrasol | Birbhum Division | Parsundi Piped Water Supply Scheme | SM/14855 | New | Withdrawing and re-sinking for 02 nos. working 200mm dia. Tubewell of 10 m depth with horizontal strainer on the river Bed of Ajoy under Parsundi Mini Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division P.H.E. Dte. | AE | JE | ORD/000513/2023-2024 | 654/BHM | 20/02/2024 | 05/04/2024 | NEEL ENTERPRISE | 2.87 | 0 | 0 | 100
3 | BIRBHUM | Khoyrasol | Birbhum Division | Parsundi Piped Water Supply Scheme | SM/14855 | New | Material Requisition To Resource Division |  |  | RTOR000247/2023-2024 | 430/BHM | 01/02/2024 | 01/02/2024 | Resource Division | 131.6 | 0 | 0 | 0
4 | BIRBHUM | Khoyrasol | Birbhum Division | Parsundi Piped Water Supply Scheme | SM/14855 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE,JE3 | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 19/07/2026 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
5 | BIRBHUM | Khoyrasol | Birbhum Division | Parsundi Piped Water Supply Scheme | SM/14855 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE,JE3 | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 29/06/2026 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
Total | [13 empty] | 5414.72 | 0 | 0