## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rajnagar | Birbhum Division | Ahmadpur Piped Water Supply Scheme | SM/14889 | New | Material Requisition To Resource Division |  |  | RTOR000151/2023-2024 | 1591/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 182.11 | 0 | 0 | 0
2 | BIRBHUM | Rajnagar | Bolpur Mechanical | Ahmadpur Piped Water Supply Scheme | SM/14889 | New | Supply and delivery of outdoor type pump controller unit for Ahamedpur and others PWSS under Rajnagar block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001221/2023-2024 | 406/Bol.MD | 07/03/2024 | 21/04/2024 | M/S. UTTAM KUMAR CHATTERJEE | 20.06 | 0 | 0 | 100
3 | BIRBHUM | Rajnagar | Bolpur Mechanical | Ahmadpur Piped Water Supply Scheme | SM/14889 | New | WBSEDCL QUOTATION FOR AHMADPUR WS SCHEME |  |  | BILL/01834/2023-2024 | BP-23-24-250 | 06/02/2024 | 06/02/2024 | WBSEDCL | 0.26 | 0 | 0 | 0
4 | BIRBHUM | Rajnagar | Bolpur Mechanical | Ahmadpur Piped Water Supply Scheme | SM/14889 | New | WBSEDCL QUOTATION FOR AHAMADPUR WATER SUPPLY SCHEME |  |  | BILL/01831/2023-2024 | BP-23-24-261 | 06/02/2024 | 06/02/2024 | WBSEDCL | 15.58 | 0 | 0 | 0
5 | BIRBHUM | Rajnagar | Birbhum Division | Ahmadpur Piped Water Supply Scheme | SM/14889 | New | Different works related to water supply scheme at AHAMADPUR & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte. 150 | AE | JE1 | ORD/000112/2023-2024 | 1877/BHM | 31/05/2023 | 17/09/2025 | B.B.C ENTERPRISE | 411.79 | 0 | 0 | 75
6 | BIRBHUM | Rajnagar | Bolpur Mechanical | Ahmadpur Piped Water Supply Scheme | SM/14889 | New | Providing Electro-mechanical accessories and others for Ahamadpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000527/2023-2024 | 2157/Bol.MD | 29/08/2023 | 04/12/2025 | SINHA ELECTRICALS | 92.12 | 0 | 0 | 70
Total | [13 empty] | 721.93 | 0 | 0