## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rajnagar | Birbhum Division | Chandrapur Piped Water Supply Scheme | SM/14893 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1455/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 110.67 | 0 | 0 | 0
2 | BIRBHUM | Rajnagar | Bolpur Mechanical | Chandrapur Piped Water Supply Scheme | SM/14893 | New | Supply & delivery of different electrical accessories at Chandrapur Piped water supply scheme under Bolpur Mechanical Division, PHE Dte.(Rajnagar Block) | Assistant Engineer-III | Junior Engineer | ORD/000584/2024-2025 | 1478./AE-III | 11/09/2024 | 18/09/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 2.11 | 0 | 0 | 100
3 | BIRBHUM | Rajnagar | Bolpur Mechanical | Chandrapur Piped Water Supply Scheme | SM/14893 | New | WBSEDCL QUOTATION FOR CHANDRAPUR WATER SUPPLY SCHEME |  |  | BILL/01833/2023-2024 | BP-23-24-260 | 06/02/2024 | 06/02/2024 | WBSEDCL | 15.71 | 0 | 0 | 0
4 | BIRBHUM | Rajnagar | Birbhum Division | Chandrapur Piped Water Supply Scheme | SM/14893 | New | Different works related to water supply scheme at CHANDRAPUR & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000026/2023-2024 | 1093/BHM | 06/04/2023 | 26/03/2025 | SADANANDA CHATTARAJ | 377 | 279.36 | 74.1 | 100
5 | BIRBHUM | Rajnagar | Bolpur Mechanical | Chandrapur Piped Water Supply Scheme | SM/14893 | New | Providing electro-mechanical accessories and others for Chanddrapur water supply scheme in Rajnagar block under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000387/2023-2024 | 1918/Bol.MD | 10/08/2023 | 02/06/2025 | A.K. INDUSTRIES | 90.43 | 27 | 29.86 | 80
Total | [13 empty] | 595.92 | 306.36 | 51.41