## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/14897 | New | Different works related to water supply scheme at GOPINATHPUR PIPED WATER SUPPLY SCHEME (TSM/016258) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000010/2023-2024 | 1091/BHM | 06/04/2023 | 06/01/2024 | M/S R B ENTERPRISE | 495.22 | 0 | 0 | 0
2 | BIRBHUM | Labpur | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/14897 | New | Material Requisition To Resource Division |  |  | RTOR000158/2023-2024 | 1601/BHM | 27/04/2023 | 27/04/2023 | Resource Division | 19.19 | 0 | 0 | 0
3 | BIRBHUM | Labpur | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/14897 | New | Continuation work Order for "Preparation & Submission of Detail Project Report (DPR) for GOPINATHPUR Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | AE | JE3 | ORD/000662/2022-2023 | 214/BSD | 31/05/2022 | 27/11/2022 | APEX ENGINEERING | 4.22 | 0 | 0 | 100
4 | BIRBHUM | Labpur | Central Drilling | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/14897 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | BIRBHUM | Labpur | Bolpur Mechanical | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/14897 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Gopinathpur PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001122/2024-2025 | 328/BOL.MD | 19/02/2025 | 19/06/2025 | M/S. UTTAM KUMAR CHATTERJEE | 74.48 | 0 | 0 | 0
Total | [13 empty] | 21932.87 | 0 | 0