## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mohammad Bazar | Birbhum Division | Dhamara Piped Water Supply Scheme. | SM/14898 | New | Material Requisition To Resource Division |  |  | RTOR000167/2023-2024 | 1621/BHM | 28/04/2023 | 28/04/2023 | Resource Division | 9.04 | 0 | 0 | 0
2 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Dhamara Piped Water Supply Scheme. | SM/14898 | New | WBSEDCL Quotation for Dhamara Piped Water Supply Scheme. |  |  | BILL/01841/2023-2024 | BP-23-24-266 | 07/02/2024 | 07/02/2024 | WBSEDCL | 3.01 | 0 | 0 | 0
3 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Dhamara Piped Water Supply Scheme. | SM/14898 | New | Empowering for new connection at Chakraipur Pump House -II in Mollarpur CCC under Bolpur Mechanical Division, PHE,Dte. |  |  | BILL/00113/2024-2025 | BP-2024-2025-50 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.52 | 0 | 0 | 0
4 | BIRBHUM | Mohammad Bazar | Birbhum Division | Dhamara Piped Water Supply Scheme. | SM/14898 | New | Different works related to water supply scheme at DHAMARA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE(HQ) | JE | ORD/000023/2023-2024 | 1244/BHM | 17/04/2023 | 17/01/2024 | ASHIM KUMAR CHAKRABORTY | 341.34 | 179.29 | 52.53 | 65
5 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Dhamara Piped Water Supply Scheme. | SM/14898 | New | Providing Electro-mechanical accessories and others for DHAMARA piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000293/2023-2024 | 1499/Bol.MD | 17/07/2023 | 01/04/2025 | UTTAM KUMAR CHATTERJEE | 28.15 | 20.97 | 74.49 | 70
6 | BIRBHUM | Mohammad Bazar | Birbhum Division | Dhamara Piped Water Supply Scheme. | SM/14898 | New | Sinking of additional T.W, Road crossing, Repairing & restoration of damaged pipe lines,sluice valve chambers including all allied works for Dhamara PWSS of Md.Bazar Development Block Under Birbhum Division, P.H.E Dte. | AE(HQ) | JE | ORD/000036/2025-2026 | 1459/BHM | 20/05/2025 | 18/08/2025 | NABIN DEBNATH | 65.66 | 0 | 0 | 0
Total | [13 empty] | 450.71 | 200.27 | 44.43