## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mohammad Bazar | Birbhum Division | Moubelia Piped Water Supply Scheme. | SM/14899 | New | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 1620/BHM | 28/04/2023 | 28/04/2023 | Resource Division | 13.88 | 0 | 0 | 0
2 | BIRBHUM | Mohammad Bazar | Birbhum Division | Moubelia Piped Water Supply Scheme. | SM/14899 | New | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 3075/BHM | 19/07/2023 | 19/07/2023 | Resource Division | 4.35 | 0 | 0 | 0
3 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Moubelia Piped Water Supply Scheme. | SM/14899 | New | Providing Electro-mechanical accessories and others for MOUBELIA piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000401/2023-2024 | 2077/BOL.MD. | 21/08/2023 | 20/10/2023 | DIPALI CONSTRUCTION | 27.4 | 26.92 | 98.23 | 80
4 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Moubelia Piped Water Supply Scheme. | SM/14899 | New | WBSEDCL QUOTATION FOR MOUBELIA WS SCHEME |  |  | BILL/01448/2023-2024 | BP-23-24-176 | 07/12/2023 | 07/12/2023 | WBSEDCL | 0.39 | 0 | 0 | 0
5 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Moubelia Piped Water Supply Scheme. | SM/14899 | New | WBSEDCL QUOTATION FOR MOUBELIA WS SCHEME |  |  | BILL/01451/2023-2024 | BP-23-24-175 | 07/12/2023 | 07/12/2023 | WBSEDCL | 4.48 | 0 | 0 | 0
6 | BIRBHUM | Mohammad Bazar | Birbhum Division | Moubelia Piped Water Supply Scheme. | SM/14899 | New | Different works related to water supply scheme at MOUBELIA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ) | JE | ORD/000009/2023-2024 | 1182/BHM | 12/04/2023 | 30/09/2024 | M/S R B ENTERPRISE | 304.55 | 244.99 | 80.44 | 100
7 | BIRBHUM | Mohammad Bazar | Birbhum Division | Moubelia Piped Water Supply Scheme. | SM/14899 | New | Sinking of additional T.W, Road crossing, Repairing & restoration of damaged pipe lines, sluice valve chambers, including all allied works for Moubelia PWSS of Md.Bazar Development Block Under Birbhum Division, P.H.E Dte | AE(HQ) | JE | ORD/000076/2025-2026 | 1639/BHM | 11/06/2025 | 09/09/2025 | M/S R B ENTERPRISE | 46.39 | 0 | 0 | 0
Total | [13 empty] | 401.45 | 271.9 | 67.73