## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Material Requisition To Resource Division |  |  | RTOR000161/2023-2024 | 1627/BHM | 28/04/2023 | 28/04/2023 | Resource Division | 35.82 | 0 | 0 | 0
2 | BIRBHUM | Labpur | Bolpur Mechanical | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Supply Delivery and Installation of automatically Voltage Correction Device at Augmentation for Bolpur SD Hospital & Bolpur water supply scheme under Bolpur Mechanical Divn. PHE Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/000582/2024-2025 | 3794/BOL.MD | 12/09/2024 | 12/10/2024 | EVEREST INFRATECH INC | 6.77 | 0 | 0 | 0
3 | BIRBHUM | Labpur | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for PUNNA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE3 | ORD/000955/2022-2023 | 305/BSD | 12/08/2022 | 10/11/2022 | APEX ENGINEERING | 1.41 | 1.14 | 80.8 | 100
4 | BIRBHUM | Labpur | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for PUNNA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.¿. | AE | JE3 | ORD/000950/2022-2023 | 266/BSD | 11/07/2022 | 07/01/2023 | APEX ENGINEERING | 4.92 | 4.11 | 83.43 | 100
5 | BIRBHUM | Labpur | Bolpur Mechanical | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Quotation for new service connection at Punna PWSS P/H- I under Ahmedpur CCC |  |  | BILL/01091/2024-2025 | BP-24-25-281 | 17/12/2024 | 17/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0 | 0
6 | BIRBHUM | Labpur | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Different works related to water supply scheme at PUNNA PIPED WATER SUPPLY SCHEME(TSM/016169) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000295/2023-2024 | 3668/BHM | 28/08/2023 | 30/10/2025 | TEKNO ENTERPRISE | 729.3 | 79.8 | 10.94 | 20
7 | BIRBHUM | Labpur | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Road restoration work for Punna Piped Water Supply Scheme, Labpur Block, under Birbhum Division, PHE Dte. | Assistant Engineer | JE2 | ORD/000190/2025-2026 | 2132/BHM | 18/08/2025 | 16/11/2025 | TEKNO ENTERPRISE | 29.63 | 0 | 0 | 0
8 | BIRBHUM | Labpur | Bolpur Mechanical | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Changing of defective sluice valve/butterfly valve on emergency basis at Gayanananda OHR site of Bolpur Projects under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000538/2024-2025 | 3793/BOL.MD | 12/09/2024 | 12/10/2024 | S.K.ELECTRICALS | 5.44 | 0 | 0 | 100
9 | BIRBHUM | Labpur | Bolpur Mechanical | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Punna PWSS (TW No II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | Assistant Engineer | Junior Engineer | ORD/001135/2024-2025 | 338/BOL.MD | 19/02/2025 | 19/06/2025 | SUNIL RABIDAS | 37.24 | 0 | 0 | 100
10 | BIRBHUM | Labpur | Central Drilling | PUNNA PIPED WATER SUPPLY SCHEME | SM/14903 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 35.83 | 0.17 | 11
Total | [13 empty] | 22195.04 | 120.88 | 0.54