## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rajnagar | Bolpur Mechanical | Patalpur Piped Water Supply Scheme | SM/14955 | New | Providing Electro-mechanical accessories and others for Patalpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000908/2023-2024 | 3552/Bol.MD | 01/12/2023 | 29/02/2024 | A. G. ENTERPRISE | 55.59 | 0 | 0 | 0
2 | BIRBHUM | Rajnagar | Bolpur Mechanical | Patalpur Piped Water Supply Scheme | SM/14955 | New | New service connection at patalpur water supply scheme under Bolpur Mechanical Division, P.H.E Dte. |  |  | BILL/01017/2024-2025 | BP-2024-25-274 | 04/12/2024 | 04/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.68 | 0 | 0 | 0
3 | BIRBHUM | Rajnagar | Birbhum Division | Patalpur Piped Water Supply Scheme | SM/14955 | New | Different works related to water supply scheme at PATALPUR & its adjoining mouzas water supply scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte | AE | JE | ORD/000350/2023-2024 | 3949/BHM | 03/10/2023 | 29/06/2024 | RAJKUMAR DAS | 89.99 | 7.27 | 8.07 | 30
Total | [13 empty] | 150.25 | 7.27 | 4.84