## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | SHEKHAMPUR PIPED WATER SUPPLY SCHEME | SM/14956 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for SHEKHAMPUR Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | AE | JE3 | ORD/000660/2022-2023 | 193/BSD | 17/05/2022 | 13/11/2022 | APEX ENGINEERING | 4.29 | 3.8 | 88.66 | 100
2 | BIRBHUM | Labpur | Central Drilling | SHEKHAMPUR PIPED WATER SUPPLY SCHEME | SM/14956 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | BIRBHUM | Labpur | Birbhum Division | SHEKHAMPUR PIPED WATER SUPPLY SCHEME | SM/14956 | New | Material Requisition To Resource Division |  |  | RTOR000156/2023-2024 | 1602/BHM | 27/04/2023 | 27/04/2023 | Resource Division | 22.21 | 0 | 0 | 0
4 | BIRBHUM | Labpur | Birbhum Division | SHEKHAMPUR PIPED WATER SUPPLY SCHEME | SM/14956 | New | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,JE1,JE3 | ORD/000084/2024-2025 | 1948/BHM | 04/07/2024 | 04/07/2027 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0 | 0
5 | BIRBHUM | Labpur | Birbhum Division | SHEKHAMPUR PIPED WATER SUPPLY SCHEME | SM/14956 | New | Erection of Sign Board (900mm X 600mm) for demarcation of land at various places under Birbhum Division, PHE Dte. | AE,AE(HQ) | Estimator,JE | ORD/000458/2024-2025 | 3608/BHM | 31/12/2024 | 31/03/2025 | IMAGIN | 40.29 | 0 | 0 | 95
6 | BIRBHUM | Labpur | Birbhum Division | SHEKHAMPUR PIPED WATER SUPPLY SCHEME | SM/14956 | New | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 2386/BHM | 27/08/2024 | 27/08/2024 | Resource Division | 10.3 | 0 | 0 | 0
7 | BIRBHUM | Labpur | Bolpur Mechanical | SHEKHAMPUR PIPED WATER SUPPLY SCHEME | SM/14956 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Sekhampur PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | Assistant Engineer | Junior Engineer | ORD/001131/2024-2025 | 336/BOL.MD | 19/02/2025 | 19/06/2025 | SATYAJIT GHOSH | 76.45 | 0 | 0 | 0
Total | [13 empty] | 23508.03 | 3.8 | 0.02