## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | BHATRA PIPED WATER SUPPLY SCHEME | SM/14958 | New | Material Requisition To Resource Division |  |  | RTOR000150/2023-2024 | 1596/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 69.42 | 0 | 0 | 0
2 | BIRBHUM | Labpur | Birbhum Division | BHATRA PIPED WATER SUPPLY SCHEME | SM/14958 | New | Different works related to water supply scheme at BHATRA PIPED WATER SUPPLY SCHEME (TSM017151) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | Assistant Engineer | JE2 ,JE3 | ORD/000305/2024-2025 | 3020/BHM | 30/10/2024 | 30/10/2025 | DIPAYAN DEY | 441.62 | 0 | 0 | 0
3 | BIRBHUM | Labpur | Birbhum Division | BHATRA PIPED WATER SUPPLY SCHEME | SM/14958 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for BHATRA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | AE | JE3 | ORD/000653/2022-2023 | 141/BSD | 07/04/2022 | 04/10/2022 | APEX ENGINEERING | 4.57 | 3.72 | 81.32 | 100
4 | BIRBHUM | Labpur | Bolpur Mechanical | BHATRA PIPED WATER SUPPLY SCHEME | SM/14958 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Bhatra PWSS (TW No I and II), Block- Labpur in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | Assistant Engineer,Assistant Engineer (HQ) | Junior Engineer | ORD/001117/2024-2025 | 325/BOL.MD | 19/02/2025 | 19/06/2025 | OSMAN SEKH | 76.34 | 0 | 0 | 0
Total | [13 empty] | 591.95 | 3.72 | 0.63