## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-II | Birbhum Division | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Continuation Work Order for Preparation & Submission of DPR for (Perkuta) Water Supply Scheme under Rampurhat-II Development Block. | AE | JE2 | ORD/000639/2022-2023 | 281/RSD | 24/08/2022 | 08/10/2022 | ECO CARE | 2.18 | 0 | 0 | 100
2 | BIRBHUM | Rampurhat-II | Birbhum Division | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1445/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 7.01 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Providing Electro-mechanical accessories and others for Parkuta PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000473/2023-2024 | 2226/Bol.MD | 12/09/2023 | 30/03/2025 | SINHA ELECTRICALS | 45.18 | 0 | 0 | 90
4 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Operation and Guarding of pumping machinery and others at Parkuta Piped Water supply Scheme (Pump House No-I(Block- Rampurhat-II) under Bolpur Mechanical Division,P.H.E Dte. |  |  | ORD/000828/2024-2025 | 1090./AE-III | 29/07/2024 | 29/08/2024 | STANDARD ELECTRICALS | 0.3 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Operation and Guarding of pumping machinery and others at Parkuta Piped Water supply Scheme (Pump House No-II(Block- Rampurhat-II) under Bolpur Mechanical Division,P.H.E Dte. |  |  | ORD/000827/2024-2025 | 1091./AE-III | 29/07/2024 | 29/08/2024 | STANDARD ELECTRICALS | 0.3 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Parkuta PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000006/2024-2025 | 686./AE-III | 08/04/2024 | 22/04/2024 | SINHA ELECTRICALS | 1.74 | 0 | 0 | 100
7 | BIRBHUM | Rampurhat-II | Birbhum Division | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Material Requisition To Resource Division |  |  | RTOR000224/2023-2024 | 221/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 2.46 | 0 | 0 | 0
8 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | wbsedcl quotation money for parkuta pwss |  |  | BILL/01430/2023-2024 | BP-23-24-150 | 04/12/2023 | 04/12/2023 | WBSEDCL | 3.99 | 0 | 0 | 0
9 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | WBSEDCL QUOTATION FOR PARKUTA P H NO.II WS SCHEME |  |  | BILL/01875/2023-2024 | BP-23-24-279 | 20/02/2024 | 20/02/2024 | WBSEDCL | 4.98 | 0 | 0 | 0
10 | BIRBHUM | Rampurhat-II | Birbhum Division | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Different works related to water supply scheme at PARKUTA & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000068/2023-2024 | 1341/BHM | 20/04/2023 | 20/10/2023 | KAZI EMDADUL HAQUE | 118.27 | 0 | 0 | 90
Total | [13 empty] | 186.41 | 0 | 0