## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. | SM/14960 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2022-2023 | 974/BHM | 27/03/2023 | 27/03/2023 | Resource Division | 183.82 | 0 | 0 | 0
2 | BIRBHUM |  | Bolpur Mechanical | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. | SM/14960 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Wells and allieds works at Augmentation of Hazarpur [( Zone-I, Pump House No - II ) and ( Zone-II, Pump House No - I & II )] Piped Water Supply Scheme, Block-Rampurhat-II under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000454/2023-2024 | 2131/Bol.MD | 25/08/2023 | 01/06/2025 | QUAZI NOZRUL ISLAM | 68.76 | 53.88 | 78.36 | 30
3 | BIRBHUM |  | Birbhum Division | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. | SM/14960 | Augmentation | Sinking of 200 mm dia Alll through and 150 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements,, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration for Zone-I & Zone- II and Providing functional household tap connection related to water supply scheme at Augmentation Of Ground Water Based Hazarpur Zone-I & Zone-II Piped Water Supply Scheme within RAMPURHAT-II Block underBIRBHUM Division, PHE Dte | AE | JE,JE3 | ORD/000435/2024-2025 | 3432/BHM | 16/12/2024 | 16/12/2025 | MONDAL& CO | 434.56 | 0 | 0 | 25
Total | [13 empty] | 687.15 | 53.88 | 7.84