## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. | SM/14960 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2022-2023 | 974/BHM | 27/03/2023 |  | Resource Division | 183.82 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. | SM/14960 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000106/2022-2023 | 1122/BHM | 10/04/2023 |  | Resource Division | 25.84 | 0 | 0 | 0
3 | BIRBHUM |  | Bolpur Mechanical | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. | SM/14960 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Wells and allieds works at Augmentation of Hazarpur [( Zone-I, Pump House No - II ) and ( Zone-II, Pump House No - I & II )] Piped Water Supply Scheme, Block-Rampurhat-II under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000454/2023-2024 | 2131/Bol.MD | 25/08/2023 | 23/11/2023 | QUAZI NOZRUL ISLAM | 68.76 | 26.94 | 39.18 | 30
Total | [13 empty] | 278.42 | 26.94 | 9.68