## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | THIBA PIPEED WATER SUPPLY SCHEME | SM/14968 | New | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 1603/BHM | 27/04/2023 | 27/04/2023 | Resource Division | 20 | 0 | 0 | 0
2 | BIRBHUM | Labpur | Birbhum Division | THIBA PIPEED WATER SUPPLY SCHEME | SM/14968 | New | Different works related to water supply scheme at THIBA PIPEED WATER SUPPLY SCHEME (TSM/017115) within Labpur Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte | Assistant Engineer | JE3 | ORD/000161/2024-2025 | 2662/BHM | 13/09/2024 | 13/09/2025 | PATHIK PABAN NANDI | 243.95 | 0 | 0 | 0
3 | BIRBHUM | Labpur | Birbhum Division | THIBA PIPEED WATER SUPPLY SCHEME | SM/14968 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for THIBA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | AE | JE3 | ORD/000661/2022-2023 | 208/BSD | 25/05/2022 | 21/11/2022 | APEX ENGINEERING | 3.16 | 2.62 | 82.73 | 100
4 | BIRBHUM | Labpur | Bolpur Mechanical | THIBA PIPEED WATER SUPPLY SCHEME | SM/14968 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Thiba PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | Assistant Engineer | Junior Engineer | ORD/001133/2024-2025 | 337/BOL.MD | 19/02/2025 | 16/10/2025 | PADMA ENGINEERING CO. | 75.59 | 0 | 0 | 40
Total | [13 empty] | 342.7 | 2.62 | 0.76