## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Khoyrasol | Birbhum Division | Demurtita Piped Water Supply Scheme. | SM/14981 | New | Preparation & Submission of DPR for Demurtita & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000674/2022-2023 | 96/BSSD | 06/06/2022 | 21/07/2022 | RADIANT | 1.59 | 1.59 | 100 | 100
2 | BIRBHUM | Khoyrasol | Birbhum Division | Demurtita Piped Water Supply Scheme. | SM/14981 | New | Material Requisition To Resource Division |  |  | RTOR000239/2023-2024 | 441/BHM | 01/02/2024 | 01/02/2024 | Resource Division | 54.82 | 0 | 0 | 0
Total | [13 empty] | 56.42 | 1.59 | 2.82