## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. | SM/15236 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2022-2023 | 1120/BHM | 10/04/2023 | 10/04/2023 | Resource Division | 20.81 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. | SM/15236 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000098/2022-2023 | 973/BHM | 27/03/2023 | 27/03/2023 | Resource Division | 81.55 | 0 | 0 | 0
3 | BIRBHUM |  | Birbhum Division | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. | SM/15236 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000231/2023-2024 | 234/BHM | 24/01/2024 | 24/01/2024 | Resource Division | 1.85 | 0 | 0 | 0
4 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. | SM/15236 | Augmentation | Quotation for new service connection at Dunigram (Zone-II) TW No-I (Block-Rampurhat-II) |  |  | BILL/02238/2023-2024 | bp-23-24-566 | 20/03/2024 | 20/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.83 | 0 | 0 | 0
5 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. | SM/15236 | Augmentation | Quotation for new service connection at Dunigram (Zone-I) TW No-III (Block-Rampurhat-II) |  |  | BILL/02237/2023-2024 | BP-23-24-307 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.64 | 0 | 0 | 0
6 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. | SM/15236 | Augmentation | Providing and Installation of Submersible pumping Machinaries at newly sunk Ground Water Based Tube Wells and allied works at Augmentation of Dunigram [( Zone-I, Pump House No - II ) and ( Zone-II, Pump House No - I & II )] Piped Water Supply Scheme, Block-Rampurhat-II under Bolpur Mechanical Division.. | Assistant Engineer-III | Junior Engineer | ORD/000453/2023-2024 | 2130/Bol.MD | 25/08/2023 | 30/06/2025 | M. S. ENTERPRISE | 76.88 | 48.48 | 63.05 | 65
7 | BIRBHUM |  | Birbhum Division | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. | SM/15236 | Augmentation | Sinking of Tubewell, Construction of OHR, Construction of Boundary wall, pump house and laying distribution system along with FHTC works at Augmentation of Ground Water Based Dunigram Zone-I & Zone-II Piped Water Supply Scheme within Rampurhat-II Block under Birbhum Division, PHE Dte. (2nd Call) | AE | JE3 | ORD/000393/2023-2024 | 4161/BHM | 30/10/2023 | 28/12/2025 | M/S GOUTAM DAS | 509.85 | 139.4 | 27.34 | 50
Total | [13 empty] | 698.41 | 187.88 | 26.9