## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Illambazar | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/15253 | New | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 1528/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 30.37 | 0 | 0 | 0
2 | BIRBHUM | Illambazar | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/15253 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for GOPINATHPUR Piped Water Supply Scheme under Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE1 | ORD/000642/2022-2023 | 137/BSD | 07/04/2022 | 06/07/2022 | M/S R DUTTA & CO. | 3.93 | 0 | 0 | 100
3 | BIRBHUM | Illambazar | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/15253 | New | Material Requisition To Resource Division |  |  | RTOR000022/2024-2025 | 2445/BHM | 30/08/2024 | 30/08/2024 | Resource Division | 10.06 | 0 | 0 | 0
4 | BIRBHUM | Illambazar | Central Drilling | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/15253 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | BIRBHUM | Illambazar | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/15253 | New | Construction 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements.Laying of Rising Main,Distribution system,including FHTC and different works related to water supply scheme at GOPINATHPUR PIPED WATER SUPPLY SCHEME (TSM/015544) within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE1 ,JE2 | ORD/000111/2024-2025 | 2165/BHM | 05/08/2024 | 05/08/2025 | KINGS & CO. | 396.77 | 0 | 0 | 10
6 | BIRBHUM | Illambazar | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME | SM/15253 | New | Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Superstructure part as per Departmental Drawing), pipe connection and cost of pipes & specials with necessary soil investigation with foundation design as per soil test report for GOPINATHPUR PIPED WATER SUPPLY SCHEMEwithin ILLAMBAZAR Block under BIRBHUM Division, PHE Dte. | Assistant Engineer | JE2 | ORD/000262/2025-2026 | 2350/BHM | 10/09/2025 | 10/09/2026 | SYED KHORSED ALAM | 85.64 | 0 | 0 | 0
Total | [13 empty] | 21866.53 | 0 | 0