## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Illambazar | Birbhum Division | MAHESWARPUR PIPED WATER SUPPLY SCHEME | SM/15254 | New | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 1584/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 20.97 | 0 | 0 | 0
2 | BIRBHUM | Illambazar | Birbhum Division | MAHESWARPUR PIPED WATER SUPPLY SCHEME | SM/15254 | New | Different works related to water supply scheme at MAHESWARPUR Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000037/2023-2024 | 1133/BHM | 10/04/2023 | 10/01/2024 | GUPTA CONSTRUCTION | 339.98 | 49.49 | 14.56 | 1
3 | BIRBHUM | Illambazar | Birbhum Division | MAHESWARPUR PIPED WATER SUPPLY SCHEME | SM/15254 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for MAHESHWARPUR Piped Water Supply Scheme under Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE2,Bolpur Sub-Division | ORD/001138/2021-2022 | 108/BSD | 21/03/2022 | 19/06/2022 | M/S R DUTTA & CO. | 2.86 | 2.66 | 93.01 | 100
Total | [13 empty] | 363.81 | 52.15 | 14.33