## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Illambazar | Birbhum Division | MAHESWARPUR PIPED WATER SUPPLY SCHEME | SM/15254 | New | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 1584/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 20.97 | 0 | 0 | 0
2 | BIRBHUM | Illambazar | Birbhum Division | MAHESWARPUR PIPED WATER SUPPLY SCHEME | SM/15254 | New | Different works related to water supply scheme at MAHESWARPUR Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000037/2023-2024 | 1133/BHM | 10/04/2023 | 10/01/2024 | GUPTA CONSTRUCTION | 339.98 | 49.49 | 14.56 | 1
3 | BIRBHUM | Illambazar | Birbhum Division | MAHESWARPUR PIPED WATER SUPPLY SCHEME | SM/15254 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for MAHESHWARPUR Piped Water Supply Scheme under Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE2,Bolpur Sub-Division | ORD/001138/2021-2022 | 108/BSD | 21/03/2022 | 19/06/2022 | M/S R DUTTA & CO. | 2.86 | 2.66 | 93.01 | 100
4 | BIRBHUM | Illambazar | Bolpur Mechanical | MAHESWARPUR PIPED WATER SUPPLY SCHEME | SM/15254 | New | New service connection at Maheswarpur PH-I W/S scheme Block - Illambazar under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/00307/2025-2026 |  | 28/04/2025 | 28/04/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.29 | 0 | 0 | 0
5 | BIRBHUM | Illambazar | Bolpur Mechanical | MAHESWARPUR PIPED WATER SUPPLY SCHEME | SM/15254 | New | Quotation for new service connection at Maheswarpur PWSS P/H - I under Illambazar CCC. |  |  | BILL/01844/2024-2025 | 115/01 | 30/07/2025 | 30/07/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.01 | 0 | 0 | 0
6 | BIRBHUM | Illambazar | Central Drilling | MAHESWARPUR PIPED WATER SUPPLY SCHEME | SM/15254 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 56.75 | 0.27 | 11
Total | [13 empty] | 21724.87 | 108.9 | 0.5