## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat-II | Birbhum Division | Dhalla Piped Water Supply Scheme | SM/15256 | New | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 1521/BHM | 26/04/2023 | 26/04/2023 | Resource Division | 55.13 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Dhalla Piped Water Supply Scheme | SM/15256 | New | Providing Electro-mechanical accessories and others for Dhalla PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000472/2023-2024 | 2225/Bol.MD | 12/09/2023 | 01/06/2025 | QUAZI NOZRUL ISLAM | 44.4 | 0 | 0 | 30
3 | BIRBHUM | Rampurhat-II | Bolpur Mechanical | Dhalla Piped Water Supply Scheme | SM/15256 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Dhalla PWSS under Illambazar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001235/2023-2024 | 520/BOL.MD | 14/03/2024 | 13/05/2024 | AMITAVA CHAKRABORTY | 7.61 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat-II | Birbhum Division | Dhalla Piped Water Supply Scheme | SM/15256 | New | Continuation Work Order for Preparation & Submission of DPR for (DHALLA) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | AE | JE3 | ORD/000787/2022-2023 | 294/RSD | 07/09/2022 | 22/10/2022 | ECO CARE | 2.76 | 0 | 0 | 100
5 | BIRBHUM | Rampurhat-II | Birbhum Division | Dhalla Piped Water Supply Scheme | SM/15256 | New | Continuation Work Order for Preparation & Submission of DPR for (DHALLA) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | AE | JE3 | ORD/000798/2022-2023 | 383/RSD | 27/09/2022 | 11/11/2022 | ECO CARE | 3.27 | 0 | 0 | 100
6 | BIRBHUM | Rampurhat-II | Birbhum Division | Dhalla Piped Water Supply Scheme | SM/15256 | New | Material Requisition To Resource Division |  |  | RTOR000041/2024-2025 | 2484/BHM | 03/09/2024 | 03/09/2024 | Resource Division | 13.92 | 0 | 0 | 0
7 | BIRBHUM | Rampurhat-II | Birbhum Division | Dhalla Piped Water Supply Scheme | SM/15256 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR , Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at DHALLA & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2,JE3 | ORD/000113/2024-2025 | 2180/BHM | 06/08/2024 | 06/08/2025 | RADIANT | 497.94 | 0 | 0 | 40
Total | [13 empty] | 625.04 | 0 | 0