## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nanoor | Birbhum Division | GOALDIHI PIPED WATER SUPPLY SCHEME | SM/15528 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for GOALDIHI Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE4 | ORD/001140/2021-2022 | 110/BSD | 22/03/2022 | 20/06/2022 | RADIANT | 3.27 | 3.03 | 92.63 | 100
2 | BIRBHUM | Nanoor | Birbhum Division | GOALDIHI PIPED WATER SUPPLY SCHEME | SM/15528 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1479/BHM | 25/04/2023 | 25/04/2023 | Resource Division | 6.64 | 0 | 0 | 0
3 | BIRBHUM | Nanoor | Birbhum Division | GOALDIHI PIPED WATER SUPPLY SCHEME | SM/15528 | New | Construction of 150 Cum. capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, laying of Rising Main ,Distribution System with FHTC and different works related to GOALDIHI PIPED WATER SUPPLY SCHEME (TSM/016090) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | Assistant Engineer | JE2 | ORD/000133/2024-2025 | 2317/BHM | 21/08/2024 | 21/08/2025 | DILIP KUMAR MONDAL | 333.62 | 0 | 0 | 0
4 | BIRBHUM | Nanoor | Bolpur Mechanical | GOALDIHI PIPED WATER SUPPLY SCHEME | SM/15528 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Goaldihi WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000970/2024-2025 | 4523/BOL.MD | 20/12/2024 | 19/04/2025 | SATYAJIT GHOSH | 75.08 | 0 | 0 | 0
5 | BIRBHUM | Nanoor | Birbhum Division | GOALDIHI PIPED WATER SUPPLY SCHEME | SM/15528 | New | Material Requisition To Resource Division |  |  | RTOR000039/2024-2025 | 2482/BHM | 03/09/2024 | 03/09/2024 | Resource Division | 6.42 | 0 | 0 | 0
6 | BIRBHUM | Nanoor | Central Drilling | GOALDIHI PIPED WATER SUPPLY SCHEME | SM/15528 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21764.78 | 3.03 | 0.01